PROJECT IMPLEMENTATION

SCHEDULING PLAN

Intelligent Operations Support System Build

Prepared by: Project Management Office

Document Type: Implementation Schedule & Resource Plan

Version: 1.0

# 1. Project Background and Objectives

An organization plans to build an “Intelligent Operations Support System” to improve internal process efficiency and knowledge management. The system covers three core modules — knowledge base management, intelligent process assistance, and quality verification — and requires integration with existing business systems. The overall build is structured as six sequential phases, described below in terms of relative duration and dependency rather than fixed calendar dates.

## Build Objectives

•  Establish a knowledge base covering core business scenarios to support the intelligent process assistance module.

•  Automate key business workflows to reduce repetitive manual effort.

•  Complete integration and deployment with existing business systems to ensure stable operation.

•  Establish a sustainable mechanism for knowledge base updates and system maintenance.

# 2. Overall Phase Structure

The project is organized into six phases, each with a defined objective, relative duration, and core deliverables. Phases proceed sequentially; a phase begins only after the prior phase’s gate review is passed.

| Seq. | Phase | Relative Duration | Objective | Key Deliverables |
| --- | --- | --- | --- | --- |
| Phase 1 | Project Initiation & Overall Planning | 2 weeks | Establish project organization and overall work plan | Implementation Plan; Project Management Guidelines |
| Phase 2 | Requirements Analysis & Solution Design | 5 weeks | Complete business scenario analysis and system solution design | Requirements Specification; System Design Document |
| Phase 3 | System Build & Knowledge Base Construction | 6 weeks | Complete core module development and initial knowledge base build | Initial Knowledge Base; Core Functional Modules |
| Phase 4 | Platform Integration & Joint Testing | 5 weeks | Complete system integration, functional testing, and defect resolution | Test Report; Integrated System |
| Phase 5 | Pilot Run & User Training | 4 weeks | Complete pilot validation and user training | Pilot Run Report; Training Materials |
| Phase 6 | Acceptance & Handover | ~4.5 weeks | Complete acceptance testing and project handover | Acceptance Report; Handover Package |

Total planning horizon: approximately 6 months, structured as a continuous sequence of the six phases above, with each phase gated by a formal review before the next phase starts.

# 3. Phase Sequencing and Dependency Structure

Rather than a calendar timeline, the schedule is represented structurally through phase sequencing and cross-phase dependencies:

| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 |
| --- | --- | --- | --- | --- | --- |
| Initiation & Planning | Requirements & Design | System Build & Knowledge Base | Integration & Testing | Pilot Run & Training | Acceptance & Handover |

Each stage above represents a sequential dependency: the next phase starts only after the preceding phase’s gate review is passed.

## Phase Gate Structure

Checkpoint before proceeding to the next phase:

| Gate | Positioned After | Exit Criteria |
| --- | --- | --- |
| Gate 1 | Phase 1 | Project organization confirmed; Implementation Plan approved |
| Gate 2 | Phase 2 | Requirements Specification and System Design Document reviewed and signed off |
| Gate 3 | Phase 3 | Initial knowledge base validated; core modules pass internal self-test |
| Gate 4 | Phase 4 | Integration testing passed; defect closure rate meets target |
| Gate 5 | Phase 5 | Pilot run indicators meet target; user training completed |
| Gate 6 | Phase 6 | Final acceptance completed; system formally handed over |

# 4. Detailed Task Breakdown by Phase

## Phase 1: Project Initiation & Overall Planning

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T1 | Project kickoff & organization confirmation | 2 days | Project Manager | — |
| T2 | Overall implementation plan & work plan development | 1 week | Project Manager / Technical Lead | T1 |
| T3 | Project management guidelines & communication protocol setup | 1 week | Project Manager | T1 |

## Phase 2: Requirements Analysis & Solution Design

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T4 | Business scenario analysis & stakeholder interviews | 2 weeks | Business Analyst | T2 |
| T5 | Requirements Specification development & review | 1.5 weeks | Business Analyst | T4 |
| T6 | System architecture & functional module design | 1.5 weeks | Technical Lead | T4 |
| T7 | Design solution review & sign-off (Gate 2) | 2 days | Project Manager / Technical Lead | T5, T6 |

## Phase 3: System Build & Knowledge Base Construction

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T8 | Knowledge base framework setup & data structuring | 2 weeks | Knowledge Engineer | T7 |
| T9 | Knowledge content collection & initial input | 3 weeks | Knowledge Engineer | T8 |
| T10 | Core functional module development | 4 weeks | Development Engineer | T7 |
| T11 | Internal self-test & initial knowledge base validation (Gate 3) | 2 weeks | Development Engineer / Knowledge Engineer | T9, T10 |

## Phase 4: Platform Integration & Joint Testing

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T12 | System integration & interface joint testing | 2 weeks | Development Engineer | T11 |
| T13 | Functional testing & defect resolution | 2 weeks | Test Engineer | T12 |
| T14 | Integration testing completion confirmation (Gate 4) | 1 week | Test Engineer / Project Manager | T13 |

## Phase 5: Pilot Run & User Training

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T15 | Pilot environment deployment & monitoring | 3 weeks | Operations Engineer | T14 |
| T16 | User training & operations manual delivery | 2 weeks | Training Specialist | T14 |
| T17 | Pilot run results evaluation & confirmation (Gate 5) | 1 week | Project Manager | T15, T16 |

## Phase 6: Acceptance & Handover

| Task ID | Task Name | Relative Duration | Responsible Role | Dependency |
| --- | --- | --- | --- | --- |
| T18 | Acceptance testing execution | 2 weeks | Test Engineer / Client Representative | T17 |
| T19 | Acceptance issue closure & documentation | 1.5 weeks | Project Manager | T18 |
| T20 | Project acceptance & handover (Gate 6) | 1 week | Project Manager | T19 |

# 5. Staffing and Resource Plan

| Role | Headcount | Primary Responsibilities | Involved Phases |
| --- | --- | --- | --- |
| Project Manager | 1 | Overall coordination, progress control, risk management | All phases |
| Business Analyst | 1–2 | Business analysis, requirements documentation | Phases 1–2 |
| Technical Lead | 1 | System architecture, technical solution oversight | Phases 2–4 |
| Knowledge Engineer | 2 | Knowledge base construction and maintenance | Phase 3 |
| Development Engineer | 3–4 | Module development, system integration | Phases 3–4 |
| Test Engineer | 2 | Functional testing, defect tracking, acceptance support | Phases 4, 6 |
| Operations Engineer | 1 | Environment deployment, pilot-run system support | Phase 5 |
| Training Specialist | 1 | User training, operations manual authoring | Phase 5 |

The project follows a dedicated Project Manager model. Core technical roles (Technical Lead, Development Engineers) remain stable from Phase 2 through Phase 4 to avoid handover loss during critical build stages. Knowledge Engineer capacity is concentrated during Phase 3 in line with knowledge base build progress.

# 6. Progress Control Measures

Weekly status review: A weekly progress meeting is held to confirm task completion status and the following week’s plan, with meeting minutes retained.

Phase gate review mechanism: Each phase gate requires a formal review; the next phase begins only after the gate is passed, preventing carry-forward of unresolved issues.

Schedule deviation escalation: A task delay exceeding 3 working days triggers an escalation and corrective action; a delay exceeding 1 week requires the Project Manager to report upward and establish a dedicated recovery plan.

Corrective actions: Standard measures include parallel task execution, temporary resource reinforcement, and compression of non-critical-path buffer time. Deviations that threaten a phase gate trigger a dedicated review and re-sequencing of subsequent tasks.

Risk register and tracking: A risk register tracks requirement changes, technical challenges, and resource conflicts, each with an assigned owner.

Combined quality and progress control: Each phase’s deliverables undergo internal quality review before being passed to the next phase, preventing quality issues from causing downstream rework and indirectly affecting the overall schedule.

# 7. Acceptance Criteria and Deliverables Checklist

| Deliverable | Corresponding Phase | Acceptance Criteria |
| --- | --- | --- |
| Implementation Plan | Phase 1 | Signed off by both parties |
| Requirements Specification | Phase 2 | Reviewed and confirmed in writing |
| Initial Knowledge Base | Phase 3 | Covers core business scenarios; content accuracy meets target |
| Core Functional Modules | Phases 3–4 | Passes functional testing; defect closure rate meets target |
| Test Report | Phase 4 | Test cases fully executed; all outstanding issues have a resolution plan |
| Training Materials & Operations Manual | Phase 5 | Covers all core operational scenarios; training completion rate meets target |
| Pilot Run Report | Phase 5 | All pilot-run indicators meet predefined targets |
| Acceptance Report | Phase 6 | Acceptance testing passed; issue list closed; signed off by both parties |